## Gantt Chart
GANTT CHART TEMPLATE | [7 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Assignment 1 | [5 empty] | COMPANY NAME | [6 empty] | Sunderland
PROJECT MANAGER |  | YCW | [5 empty] | DATE | [6 empty] | 2022-05-05
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | Deliverables | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Assignment 1
1.1 | project charter | YCW | 2022-05-05 | 2022-05-12 | 5 | 100% | gantt chart | bar: WEEK 1 M to WEEK 1 F
1.2 | business & domain study | YCW | 2022-05-12 | 2022-05-19 | 5 | 0% | topic
1.2.1 | - Business study | YCW | 2022-05-12 | 2022-05-17 | 3 | 0% | business model | bar: WEEK 2 M to WEEK 2 W
1.2.2 | - Application area | YCW | 2022-05-17 | 2022-05-19 | 2 | 0% | The product | bar: WEEK 2 R to WEEK 2 F
1.3 | Data sourcing | YCW | 2022-05-19 | 2022-05-26 | 5 | 0% | dataset | bar: WEEK 3 M to WEEK 3 F
1.4 | literature research | YCW | 2022-05-26 | 2022-06-02 | 5 | 0% | ideas | bar: WEEK 4 M to WEEK 4 F
1.4.1 | - 'Comparision of data science methodology | YCW | 2022-05-26 | 2022-05-31 | 3 | 0% | Methodology | bar: WEEK 4 M to WEEK 4 W
1.4.2 | - Comparision of machine learning model | YCW | 2022-05-31 | 2022-06-02 | 2 | 0% | Target ML model | bar: WEEK 4 R to WEEK 4 F
1.3 | Comparision of software tools | YCW | 2022-06-02 | 2022-06-09 | 5 | 0% | Tools list
1.4 | Conclusion | YCW | 2022-06-09 | 2022-06-16 | 5 | 0% | Conclusion | bar: WEEK 6 M to WEEK 6 F
1.5 | Project discussion | YCW | 2022-06-16 | 2022-06-23 | 5 | 0% | Topic confirmation | bar: WEEK 7 M to WEEK 7 F
1.5 | Report writing | YCW | 2022-06-23 | 2022-07-07 | 10 | 0% | Completed assignment | bar: WEEK 8 M to WEEK 9 F
Formulas:
DUE DATE = WORKDAY([START DATE],[DURATION])
START DATE = [DUE DATE, row above]