## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Assignment 2 | [5 empty] | COMPANY NAME | [6 empty] | Sunderland
PROJECT MANAGER |  | YCW | [5 empty] | DATE | [6 empty] | 2022-05-05
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | Deliverables | PHASE ONE - Requirement | [19 empty] | PHASE TWO - Implementation | [14 empty] | Verification |  |  |  |  | PHASE FOUR - Documentation
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Assignment 2
1.1 | Business & domain study | YCW | 2022-05-05 | 2022-05-12 | 5 | 100% | gantt chart | bar: WEEK 1 M to WEEK 1 F
1.2 | Data sourcing | YCW | 2022-05-12 | 2022-05-19 | 5 | 100% | dataset | bar: WEEK 2 M to WEEK 2 F
1.3 | literature research | YCW | 2022-05-19 | 2022-05-26 | 5 | 100% | topic and ideas | bar: WEEK 3 M to WEEK 3 F
1.4 | Define product requirements | YCW | 2022-05-26 | 2022-06-02 | 5 | 100% | requirements | bar: WEEK 4 M to WEEK 4 F
1.5 | Comparison of data science methodology | YCW | 2022-06-02 | 2022-06-09 | 5 | 100% | methodology | bar: WEEK 5 M to WEEK 5 F
1.6 | Code implementation | YCW | 2022-06-09 | 2022-06-23 | 10 | 100% | Code & software product | bar: WEEK 6 M to WEEK 7 F
1.7 | Product verification test | YCW | 2022-06-23 | 2022-06-30 | 5 | 100% | Test result | bar: WEEK 8 M to WEEK 8 F
1.8 | Report writing | YCW | 2022-06-30 | 2022-07-14 | 10 | 100% | Completed report | bar: WEEK 9 M to WEEK 10 F
Formulas:
DUE DATE = WORKDAY([START DATE],[DURATION])
START DATE = [DUE DATE, row above]